MILO

8-Week Marketing Plan

April 7 to June 1, 2026  |  Instagram + WhatsApp  |  Beta launch: End of June  |  Exams: All of May

The strategic reality

May is a dead zone for production. That means April has to do double the work — build momentum AND batch all May content in advance. The team that doesn't batch in April will go silent in May and lose everything they built.

The plan accounts for this. Weeks 3 and 4 are the most important weeks in this entire document.

Phase overview

Weeks 1-2  Ignition — website live, groups seeded, first reels, momentum starts

Weeks 3-4  Build + batch — grow community, lock 6-week plan, batch ALL May content

Weeks 5-7  Exam mode — pre-made content only, WhatsApp kept warm, team on exams

Week 8     Pre-launch — team back, hype engine on, beta countdown begins

Week by week

| Week | Dates | Phase | Instagram | WhatsApp | Goal | Load |
| --- | --- | --- | --- | --- | --- | --- |
| W1 | Apr 7-13 | Ignition | 3 reels: city event highlights + first FOMO hook. 1 brand intro post. Daily stories. | All 3 city groups seeded. First curated events dropped. Interns start adding members. | Website live Monday. First reel posted. Groups active in Delhi, Mumbai, Bangalore. | HIGH |
| W2 | Apr 14-20 | Ignition | 3 reels: 'you missed this' recaps. 2 posts: Milo positioning. Poll stories. | 3 events per city this week. Ask members: what events do you want to see? | 50+ WhatsApp members across all cities. 200+ Instagram followers. Templates finalised. | HIGH |
| W3 | Apr 21-27 | Build + batch | 2 reels live. BATCH 4 reels for May (exam weeks). 2 posts scheduled. | Events 3x per week. Community list of 15 names per city due this week. | All May content batched and scheduled. 6-week plan locked. Lists done. | HIGH |
| W4 | Apr 28-May 4 | Build + batch | 2 reels live. BATCH remaining May content + 2 pre-launch teaser reels. | Events 3x per week. Intern output reviewed. Gaps filled by core team. | 100% of May content ready to go. Team briefed. Nothing needs making during exams. | HIGH |
| W5 | May 5-11 | Exam mode | 1 pre-made reel goes out. Stories 2-3x. Zero new production. | 1 event drop per city. Prapti manages. No team pressure. | Stay visible. Don't go silent. Team fully focused on exams. | LOW |
| W6 | May 12-18 | Exam mode | 1 pre-made reel. Stories only. Scheduled posts auto-publish. | 1 event drop per city. Minimum viable presence. | Community stays warm. No churn. Exams first. | LOW |
| W7 | May 19-25 | Exam mode | 1-2 pre-made reels. Stories. Begin subtle beta teaser if exams allow. | 1-2 event drops per city. Drop a hint: 'something is coming soon.' | Keep groups curious. Plant seeds for launch hype. Still low load. | LOW |
| W8 | May 26-Jun 1 | Pre-launch | 3 reels: beta countdown, app teaser, FOMO hook. Daily stories. Full comeback. | Announce beta is coming end of June. Exclusive early access messaging starts. | Exams done. Full team back. Hype engine switched on. Waitlist building. | HIGH |

Content playbook

Six content types that repeat across the 8 weeks. Every piece of content maps to one of these. No improvising.

| Content type | What it looks like |
| --- | --- |
| FOMO hook reel | 'You missed this Saturday' — event recap, aesthetic visuals, music. No talking head. Under 30 sec. |
| Coming soon reel | Midnight navy + gold Milo branding. Short teaser. No product demo yet. Mystery over clarity. |
| City event post | Clean graphic: event name, date, venue. Consistent Milo template. Posted Mon / Wed / Fri. |
| Community spotlight | 'This is who's already in the Milo community' — makes others want to join. |
| Beta countdown | Starts Week 8. Daily story countdown. Early access drops in WhatsApp groups 24hrs before Instagram. |
| Behind the scenes | Team working, interns on campus, groups growing. Makes it feel real, not corporate. |

Non-negotiable rules

| Batch May content in April | Weeks 3 and 4 are the only window. If it isn't made by Apr 27, May goes dark. |
| --- | --- |
| WhatsApp never goes silent | Even during exams — 1 event per city per week minimum. Prapti owns this in May. |
| Quality over quantity | 2 great reels beat 5 average ones every time. Slow weeks are fine. Bad content isn't. |
| Early access = exclusive | Beta link drops in WhatsApp groups 24hrs before Instagram. Members feel VIP. |
| Anadi owns execution | Ayan sets direction. Anadi makes it happen. Friday call is the checkpoint. |
| No new initiatives in May | Zero new campaigns, zero new platforms, zero new ideas until June. Execute only. |

What success looks like by end of Week 8

WhatsApp: 200+ members combined across Delhi, Mumbai, Bangalore. Groups feel alive.

Instagram: 500+ followers, strong reel engagement, brand identity clear.

Content: All June launch content is being planned now — not made in a panic.

Community: 100+ people who have been warm for 8 weeks waiting for beta access.

Owned by Anadi (marketing lead). Reviewed with Ayan every Friday 10 PM.