MILO

Weekly Task Sheet

Week of April 21, 2026  —  Pre-launch execution phase

Context this week

Last week saw good progress from parts of the team but Minhaj, Arka, Shashank, Rushiketh, and Mujammil are carrying backlog. That backlog runs alongside this week's work — no dropping old tasks to pick up new ones.

This week splits into two tracks: things due by Wednesday and things due by Friday. Wednesday is not a soft deadline.

Due by Wednesday

These five tasks must be done before Wednesday's check-in. If blocked, message Anadi by Tuesday night.

| Person | Task | What done looks like | Deadline |
| --- | --- | --- | --- |
| Riddhi + Pavani | Incubator collab — identify targets together, align on pitch angle, initiate first outreach | List of incubators approached + outreach message sent to at least one | Wednesday |
| Prapti + Gayatri | First post: 'Not Everyone Gets A Stage' — story-based post with research, graphs, images, addressable market, and the problem Milo solves | Designed post ready for Ayan review — not just a draft, a finished visual | Wednesday |
| Ishaan | Build a link tracker — for every link posted across WhatsApp groups, track who posted it, which group, and how people reacted | Working tracker shared (Google Sheet or Notion) with columns: link, group, posted by, reactions/clicks | Wednesday |
| Shashank | Reddit ghost post — post on r/delhi about a real upcoming Delhi event, mention in description that you found out about it from the Milo WhatsApp group | Live Reddit post link shared in team group | Wednesday |
| Aamya + Bhupati | Second post: research-based post on how the event industry works in India and how Milo is changing it | Designed post ready for Ayan review | Wednesday |

Tech team — whole week

| Person | Task | What done looks like | Deadline |
| --- | --- | --- | --- |
| Minhaj + Arka | M series bugs — work through backlog + this week's M1 to M7 milestones, skip M6 | Progress update Wednesday check-in, completed items marked in brain.md by Friday | Friday |
| Shashank | Backlog UI fixes from last week still pending — carry over all unfinished items alongside Reddit task | Each fix confirmed with before/after screenshot by Friday | Friday |

Community interns — whole week

Evaluated at both Wednesday check-in and Friday meeting. Each city has a clear number target. Screenshots are the only proof accepted.

| Person | Task | What done looks like | Deadline |
| --- | --- | --- | --- |
| Vishwajeet, Manasvi, Pooja, Shardul (Delhi) | Delhi already hit 10 — add 5 more members this week + post 5 event links in the group | Screenshot: group count + 5 event posts visible in group chat | Wed check-in + Friday |
| Ramesh, Mujammil, Rushiketh (Bangalore) | Hit 10 member target + post 5 event links in group — backlog from last week applies | Screenshot: 10 members in group + 5 event posts visible | Wed check-in + Friday |
| Himika, Anushka (Mumbai) | Hit 10 member target + post 5 event links in group | Screenshot: 10 members in group + 5 event posts visible | Wed check-in + Friday |

City intern roster — updated

Delhi: Vishwajeet, Manasvi, Pooja, Shardul

Bangalore: Ramesh, Mujammil, Rushiketh

Mumbai: Himika, Anushka (new)

Check-in cadence

Wednesday — one update per person in group chat. Community interns post screenshots. Core team posts task status. Prapti collects and flags blockers to Anadi.

Friday 10 PM — full team call. Progress, blockers, next week tasks. Ayan chairs, Anadi tracks.

From Ayan — CEO, Milo

Good work from those who delivered last week. For those carrying backlog — this week is the week to clear it. Don't let it follow you into next week.